## Sheet1
ID | Name | Start Date | End Date | Duration | Progress % | Dependency | Resources | Color
1 | Project Initiation Phase | 2023-03-03 08:00 | 2023-04-06 17:00 | 25 days | 100
2 | Define project scope and objectives | 2023-03-03 08:00 | 2023-03-16 17:00 | 10 days | 100 |  | Team Member 1 | 121
3 | Conduct market research and competitor analysis | 2023-03-17 08:00 | 2023-03-23 17:00 | 5 days | 100 | 2FS | Team Member 2 | 211
4 | Create a project plan and allocate resources | 2023-03-24 08:00 | 2023-04-06 17:00 | 10 days | 100 | 3FS | Team Member 3 | 301
5 | Design Phase | 2023-04-07 08:00 | 2023-05-11 17:00 | 25 days | 100
6 | Designing the app's features and functionalities | 2023-04-07 08:00 | 2023-04-20 17:00 | 10 days | 100 | 4FS |  | 121
7 | User interface (UI) and user experience (UX) design | 2023-04-21 08:00 | 2023-05-11 17:00 | 15 days | 100 | 6FS
8 | Database design and architecture planning | 2023-04-21 08:00 | 2023-05-04 17:00 | 10 days | 100 | 6FS |  | 301
9 | Development Phase | 2023-05-05 08:00 | 2024-03-22 17:00 | 231 days | 100
10 | Documentations (Tech Stacks and Rules) | 2023-05-05 08:00 | 2023-06-08 17:00 | 25 days | 100 | 8FS |  | 121
11 | Backend development | 2023-06-09 08:00 | 2023-08-15 17:00 | 48 days | 100
12 | Set up the server and database | 2023-06-09 08:00 | 2023-06-30 17:00 | 16 days | 100 | 10FS
13 | Implement APIs for recipes, workouts, and user interactions | 2023-07-03 08:00 | 2023-07-24 17:00 | 16 days | 100 | 12FS |  | 181
14 | Integrate third-party tools for food photo recognition and nutrition data | 2023-07-25 08:00 | 2023-08-15 17:00 | 16 days | 100 | 13FS |  | 211
15 | Frontend development | 2023-07-25 08:00 | 2023-10-20 17:00 | 64 days | 100
16 | Implement UI/UX designs | 2023-07-25 08:00 | 2023-09-28 17:00 | 48 days | 100 | 13FS |  | 301
17 | Develop user registration and login functionality | 2023-08-16 08:00 | 2023-10-20 17:00 | 48 days | 100 | 14FS |  | 331
18 | Create recipe and workout browsing interfaces | 2023-08-16 08:00 | 2023-10-20 17:00 | 48 days | 100 | 14FS |  | 31
19 | Implement user connectivity features | 2023-08-16 08:00 | 2023-10-20 17:00 | 48 days | 100 | 14FS |  | 61
20 | Testing Phase | 2023-10-23 08:00 | 2023-12-22 17:00 | 45 days | 100
21 | Conduct unit testing for individual components | 2023-10-23 08:00 | 2023-11-10 17:00 | 15 days | 100 |  |  | 121
22 | Perform integration testing for the entire application | 2023-11-13 08:00 | 2023-12-01 17:00 | 15 days | 100 | 21FS
23 | Test the food photo recognition and nutrition information feature | 2023-12-04 08:00 | 2023-12-22 17:00 | 15 days | 100 | 22FS |  | 301
24 | Beta Testing | 2023-12-25 08:00 | 2024-03-22 17:00 | 65 days | 100
25 | Release a beta version of the app to a limited number of users | 2023-12-25 08:00 | 2024-01-12 17:00 | 15 days | 100 | 23FS |  | 121
26 | Collect feedback and identify areas for improvement | 2024-01-15 08:00 | 2024-02-29 17:00 | 34 days | 100
27 | Address bugs and issues reported during beta testing | 2024-03-01 08:00 | 2024-03-22 17:00 | 16 days | 100 | 26FS |  | 301
28 | Deployment Phase | 2024-03-25 08:00 | 2024-05-03 17:00 | 30 days | 100
29 | Prepare the app for public release | 2024-03-25 08:00 | 2024-04-05 17:00 | 10 days | 100 | 27FS |  | 121
30 | Launch the SmartEats app on app stores (iOS and Android) | 2024-04-08 08:00 | 2024-04-19 17:00 | 10 days | 100
31 | Monitor the app's performance and user feedback post-launch | 2024-04-22 08:00 | 2024-05-03 17:00 | 10 days | 100 | 30FS |  | 301